## Blad1
Planning ( what needs to be done? ) | Time Spent | Status | Notes
Start project ( making all scripts and setting up scene ) | 1:30 | DONE
Writing structure in scripts ( members and functions ) | 2:00 | DONE | Did it in parts, most of the structure stuff is done
Creating Unity UI with default Character ( test ) | 0:40 | DONE
Writing managers ( game, character, UI ) |  | BUSY | UIManager not entirely clear, UI seems to work without it
Writing character ( = visualize the prefab and spawn it in level with correct stats ) |  | /
Spawn 3 test characters | 0:20 | DONE
Spawn 3 characters | 1:00 | DONE
Setting camera |  | /
Writing enemy |  | /
Set level and enemy positions |  | /
Weapon stats altering | 0:20 | DONE
UI | 1:50 | DONE
Health of characters and enemies |  | /
Panels with info ( weapons, health, name ) | 0:30 | DONE
End game condition ( win/lose ) |  | /
Let characters follow selected character ( no clipping -> navmesh ) |  | /
Let enemies track ( follow ) selected character ( no clipping -> navmesh ). When close enough, attack closest of 3 characters |  | /