## Blad1
Planning ( what needs to be done? ) | Time Spent | Status | Notes
Start project ( making all scripts and setting up scene ) | 1:30 | DONE
Writing structure in scripts ( members and functions ) | 2:00 | DONE | Did it in parts, most of the structure stuff is done
Creating Unity UI with default Character ( test ) | 0:40 | DONE
Writing managers ( game, character, UI ) |  | BUSY
Writing character |  | /
Spawn 3 test characters | 0:20 | DONE
Spawn 3 characters |  | /
Setting camera |  | /
Writing enemy |  | /
Set level and enemy positions |  | /
Weapon stats altering |  | /
UI |  | /
Health of characters and enemies |  | /
Panels with info ( weapons, health, name ) |  | /
End game condition ( win/lose ) |  | /