## Blad1
Planning ( what needs to be done? ) | Time Spent | Status | Notes
Start project ( making all scripts and setting up scene ) | 1:30 | DONE
Writing structure in scripts ( members and functions ) | 2:00 | DONE | Did it in parts, most of the structure stuff is done
Creating Unity UI with default Character ( test ) | 0:40 | DONE
Writing managers ( game, character, UI ) | 3:15 | DONE | UIManager not entirely clear, UI seems to work without it
Character manager | 3:00 | DONE | I did it in parts and added some small methods later on ( because of how I made the enemies etc. )
UI Manager | 0:15 | DONE
Writing character ( = visualize the prefab and spawn it in level with correct stats ) | 2:30 | DONE | No direct link between UI and logic yet, but can easily add it, not necessary yet
Spawn 3 test characters | 0:20 | DONE
Spawn 3 characters | 1:00 | DONE
Setting camera | 0:45 | DONE
Writing enemy | 2:00 | DONE
Set level and enemy positions | 0:45 | DONE
Weapon stats altering | 0:20 | DONE
Weapon visuals and implementation ( behaviour ) | 1:50 | DONE | Sword only works within range of enemy, Ranger shoots his arrows, Wizard can only heal
UI | 1:50 | DONE
Health of characters and enemies | 2:30 | DONE
Panels with info ( weapons, health, name ) | 0:30 | DONE
End game condition ( win/lose ) | 0:20 | DONE
Let characters follow selected character ( navmesh ) | 1:00 | DONE
Basic enemy movement ( navmesh agents ) | 0:10 | DONE
Let enemies track ( follow ) selected character ( navmesh ). | 2:00 | DONE | Now enemy tracks always selected character, I need a check to see if one of the enemies is close enough
When close enough, attack closest of 3 characters | 0:25 | DONE
Revisit end game, more elegant solution | 1:30 | DONE | This cost me a lot of time due to testing
Inventory ( panel ) | 0:10 | DONE | Seperated character panel and inventory panel ( put actual items on the inventory panel )
Added menu screen with info | 0:20 | DONE
Cleanup code | 0:00 | DONE | I'll keep on cleaning until deadline